# Operations Analytics Formula Cheatsheet

This document contains all formulas, thresholds, slabs, logic, and operational intelligence calculations currently implemented in the HRMS & Operations Management Suite analytics architecture.

## 1. Task Completion Formula

Formula / Logic: Completion % = (Closed Tasks / Total Tasks) × 100

Closed task status: closed

Open task: any status except closed

Used in Project Intelligence, KPI cards, Employee Analytics

## 2. Overdue Task Logic

Formula / Logic: Task is overdue if: deadline < current date AND status != closed

Used in Project Health, Executive Insights, Resource Intelligence

Overdue tasks are ignored if status is closed

## 3. Project Health Classification

Formula / Logic: Health slabs based on overdue task count

Healthy = 0 overdue tasks

At Risk = 1 to 3 overdue tasks

Critical = 4+ overdue tasks

## 4. Resource Utilization Formula

Formula / Logic: Utilization % = (Tracked Hours / Allocated Hours) × 100

Tracked duration source: task_logs.duration

Duration stored in seconds

Hours conversion = seconds / 3600

Underutilized ≤ 20%

Healthy = 21% to 119%

Overloaded ≥ 120%

## 5. Burnout Risk Detection

Formula / Logic: Burnout risk triggered using active tasks and recent tracked hours

Active tasks threshold ≥ 10

Recent tracked hours threshold ≥ 35 hours in last 7 days

## 6. Dependency Risk Detection

Formula / Logic: Dependency Contribution % = (Employee Contribution / Total Project Contribution) × 100

Risk triggered when one employee contributes ≥ 70%

## 7. Productivity Drop Detection

Formula / Logic: Current Week Productivity < Previous Week Productivity × 0.5

Previous week minimum baseline = 10 hours

Current week below 50% of previous week triggers decline

## 8. Backlog Growth Risk

Formula / Logic: New Tasks > Closed Tasks × 1.5

150% growth threshold

Indicates operational backlog increase

## 9. Deadline Failure Prediction

Formula / Logic: Predictive trigger conditions

Overdue tasks ≥ 3

Completion ≤ 50%

2+ tasks near deadline within next 3 days

## 10. Top Performer Ranking

Formula / Logic: Efficiency % = (Closed Tasks / Assigned Tasks) × 100

Employees with 0 assigned tasks excluded

Sorted by highest efficiency

## 11. Department Efficiency

Formula / Logic: Department Efficiency % = (Closed Tasks / Total Department Tasks) × 100

Department mapping uses assigned_to relation

## 12. Tracked Time Aggregation

Formula / Logic: Hours = Seconds / 3600

Source column: task_logs.duration

Stored in seconds

Display formatting handled via formatDuration()

## 13. Resource Status Classification

Formula / Logic: Classification based on workload and utilization

Overloaded = 10+ active tasks OR 120%+ utilization

Underutilized = ≤1 active task AND ≤20% utilization

Healthy = everything else

## 14. Near Deadline Detection

Formula / Logic: Task considered near deadline if deadline ≤ 3 days

Used in predictive deadline analysis

## 15. Executive Overview Metrics

Formula / Logic: Current executive insight cards

Critical Projects

Burnout Risk

Resource Dependency

Overdue Tasks

These are operational summaries, not predictive AI